## Sheet1
1月份安排
第一周 | 第二周 | 第三周 | 第四周 | 第五周
12.27-12.31 | 1.2-1.6 | 1.9-1.13 | 1.16-1.20 | 1.24-1.28
Step1: sort out the framework with Li Feng and ask for the source code; step2: Purchase development board kits and other equipment | Step3: Sort out the deficiencies of existing solutions (temporarily think of what problems are encountered in image segmentation, whether it affects recognition? Is there any defect in the accuracy of AOA algorithm? The recognition accuracy of one-to-many experiments? Extend to general Bluetooth devices) | step4: Discuss and redesign the experimental plan, including development board, mobile edge computing module, general bluetooth device expansion, one-to-many recognition experiment, etc. | Step5: Use the mobile app to call the API, expand from the development board to the general mobile application platform; design plan | Summarize the work and check for gaps
2月份安排
第一周 | 第二周 | 第三周 | 第四周
1.30-2.3 | 2.6-2.10 | 2.13-2.17 | 2.20-2.24 | 备注
step6: Build the hardware platform; step7: Offload design of mobile edge computing; Step8: One-to-many experimental design. | step6: Build the hardware platform; step7: Offload design of mobile edge computing; Step8: One-to-many experimental design. | step6: Build the hardware platform; step7: Offload design of mobile edge computing; Step8: One-to-many experimental design. | Summarize the work and check for gaps
3月份安排
第一周 | 第二周 | 第三周 | 第四周 | 第五周
2.27-3.3 | 3.6-3.10 | 3.13-3.17 | 3.20-3.24 | 3.27-3.31
step9: experimental tests | step9: experimental tests | step10: Recognition experiment of other bluetooth devices; | step10: Recognition experiment of other bluetooth devices; | Summarize the work and check for gaps
4月份安排
第一周 | 第二周 | 第三周 | 第四周
4.3-4.7 | 4.10-4.14 | 4.17-4.21 | 4.24-4.28 | 备注
Step12: Organize the experimental results, design the structure of the paper, and form a framework. | step13：Complete the first draft | step14：revirevise the paper | step14：revise the paper
5月份安排
第一周 | 第二周 | 第三周 | 第四周
5.1-5.5 | 5.8-5.12 | 5.15-5.19 | 5.22-5.26 | 备注
step15：submit the paper | reserve delay time | reserve delay time | 。。。